## Gantt Template
CIVE 202 – Civil Engineering Analysis II | [6 empty] | Project #4 – Gantt Chart Template
Group Members | Max Smith | [5 empty] | Legend
Project Start Date | 2026-04-01 | [5 empty] | Fill dates and task owners.
Project Due Date | 2026-04-21 | [5 empty] | Blue cells = scheduled work
States Analyzed | Colorado and Texas | [5 empty] | Orange row = milestone / deliverable
Notes | Adjust tasks/dates as needed to match your scope of work
Task ID | Major Task / Deliverable | Owner(s) | Predecessor | Start Date | End Date | Duration | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21
[7 empty] | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
1 | Download NRI data for State 1 and State 2 | Max Smith |  | 2026-04-20 | 2026-04-20 | 1 | bar: Mon
2 | Download metadata files and review variables | Max Smith | 1 | 2026-04-20 | 2026-04-20 | 1 | bar: Mon
3 | Download SVI dataset / external source | Max Smith | 1 | 2026-04-20 | 2026-04-20 | 1 | bar: Mon
4 | Clean and organize tract-level datasets | Max Smith | 1,2,3 | 2026-04-20 | 2026-04-20 | 1 | bar: Mon
5 | Join datasets and handle missing / NA values | Max Smith | 4 | 2026-04-20 | 2026-04-20 | 1 | bar: Mon
6 | Define alternative risk method | Max Smith | 4,5 | 2026-04-20 | 2026-04-20 | 1 | bar: Mon
7 | Write Python code and test calculations | Max Smith | 5,6 | 2026-04-20 | 2026-04-20 | 1 | bar: Mon
8 | Create tables / figures comparing NRI vs. new method | Max Smith | 7 | 2026-04-21 | 2026-04-21 | 1 | bar: Tue
9 | Generate GeoPandas map | Max Smith | 7,8 | 2026-04-21 | 2026-04-21 | 1 | bar: Tue
10 | Write Scope of Work | Max Smith |  | 2026-04-21 | 2026-04-21 | 1 | bar: Tue
11 | Write annotated code document | Max Smith | 7 | 2026-04-21 | 2026-04-21 | 1 | bar: Tue
12 | Complete report / interpretation write-up | Max Smith | 8,9,11 | 2026-04-21 | 2026-04-21 | 1 | bar: Tue
13 | Finalize GitHub repository and submission files | Max Smith | 10,11,12 | 2026-04-21 | 2026-04-21 | 1 | bar: Tue

## Instructions
How to Use This Gantt Chart Template
1. Fill in group member names, project start date, due date, and states on the Gantt Template sheet.
2. Enter each task owner, start date, and end date. The duration column calculates automatically.
3. Blue bars appear automatically when the task dates line up with the project calendar.
4. Change, delete, or add tasks so the chart matches your actual scope of work.
5. Use this chart to show major project tasks, durations, dependencies, and a clear start/end timeline.
6. Keep the chart consistent with your Scope of Work and final project submission.
Suggested major tasks from the project prompt:
• Download NRI data for two states
• Review metadata and variable definitions
• Download SVI dataset / outside sources
• Clean, organize, and merge datasets
• Handle missing values
• Build and test alternative risk method
• Create figures / summary tables
• Generate at least one GeoPandas map
• Prepare Scope of Work, ACD, report, GitHub repo, and final submission files